## Instructions
Project Risk Assessment Form
INSTRUCTIONS are below (click the tab at the bottom of the screen to access the Project Risk Assessment Form)
1. List your project risks.
2. For each risk listed, add the likelihood of the risk occurring and its potential impact (use high, medium, or low).
3. For each risk, determine your risk response strategy (avoid, transfer, mitigate, or accept the risk).
4. Then document the actions required, responibilities, due dates and when completed.
The worksheet is completely flexible. Rows and columns may be resized. Data may be amended. Additional worksheets may be added.

## Project Risk Assessment Form
Seq No. | Risk | Likelihood (eg High, Medium, Low) | Impact (eg High, Medium, Low) | Risk Response Strategy (eg Avoid, Transfer, Mitigate, or Accept risk) | Actions Required | Responsible Person | Due Date | Done
1 | Errors in code | Medium | High | Mitigate | Refer documentation and find the exact solutions | Everyone | 17/4/21 | yes
2 | Not meeting deadlines | Low | High | Avoid | Stick to the project plan | Naveed
3 | Issues with connecting to the database | Low | High | Avoid | Consult with a resource person | Ashan
4 | Inadequate risk management | Low | High | Mitigate | Maintaing the Risk Assessment Form by properly identifying the potential risks | Dewni | 2021-03-24 | yes
5 | Technical Difficulties | High | High | Mitigate | Explore new technologies | Isuru | 2021-03-24 | yes
6 | Inability to get the 100% participation for the team meetings | Low | Medium | Avoid | Sheduling the meetings in advance | Shathurthika | 2021-03-28 | yes
7 | Insufficient experience in Software Projects | High | High | Mitigate | Selfstudy and increase experience | All | 15/4/21 | yes
8 | Insufficient Data | Medium | Medium | Mitigate | Get data from existing databases | Panuja | 2021-09-04 | yes
.

## Risk Matrix
Impact
|  | Low |  |  |  | High
| High |  |  |  | 5 | 7 | Risk
|  |  |  | 1 |  |  | Low
Likelihood |  |  |  | 8 | 4 |  | Medium
|  |  |  | 3 |  | 2 | High
| Low |  |  | 6